## Year-End
State of Wisconsin
FY 2019 Year-End Closing and Reconciliation Task List |  |  |  |  | SCO Task
Last Updated 07/09/2019 |  |  |  |  | Agency Task
Module or Fiscal Year closing
No. | Entity | Task | Task Details | Due
1 | SCO | Continuing KK to GL reconciliation of expenditures, adjusting entries made. | This is an ongoing task. Any differences as of 6/30 will be adjusted by the SCO by 7/12. The SCO will then run weekly reconciliations as of each Friday (7/12, 7/19, 7/26 , 8/2, 8/9) making the adjusting entries by the following Wednesday (three days later). Agencies will be notified of all adjusting entries as they are made. NOTE: FY 2019 will be closed for Non-Project agencies on Friday, 8/2. So, the Friday, 7/26 KK to GL reconciliation should be the final substantive reconciliation before closing. The SCO will make a final check of all Non-Project agencies on Friday 8/2 to ensure that no additional issues were introduced that week. For Project Agencies, the final reconciliation will be 8/2, with a final check on 8/9. | ongoing
2 | SCO | Continuing analysis and reconciliation of Collected Revenue (CC_REV_COL) ledger. | This is an ongoing task. Any differences as of 06/30/2019 will be adjusted by SCO by 07/12/2019. This SCO will then run weekly reconciliations as of each Friday (07/12, 07/19, 07/26, 08/02, and 08/09) making the adjusting entries by the following Wednesday (three days later). Agencies can retreive these adjusting entries and the SCO's analysis by accessing the "Collected Revenue Analysis Register" available on the FY 2019 Closing page of the DOA website. NOTE: FY 2019 will be closed for Non-Project agencies on Friday, 8/2. So, Friday 07/26, Collected Revenue reconciliation should be the final substantive reconciliation before closing. The SCO will make a final check of all Non-Project agencies on Friday 8/2 to ensure that no additional issues were introduced that week. For Project Agencies, the final reconciliation will be 8/2, with a final check on 8/9. | ongoing
3 | Agency | Process all open vouchers, journals, interunit transactions as June 30th (see monthly SCO checklist). | See Section 18-01 of the Wisconsin Accounting Manual | 2019-07-05
4 | Agency | Review trial balance and flag accounts that appear incorrect. Created inventory of all clearing appropriations that need adjusting/correcting entries. | Reconciliation - Approach to Trial Balance Validation | 2019-07-05
5 | SCO | Life insurance expenditures reclassified to prepaids for pay period 12A. | SCO processes reclassification entries for life insurance only, as these amounts are not paid until July. | 2019-07-10
6 | SCO | Life insurance expenditures reclassified to prepaids for pay period 13B. | SCO processes reclassification entries for life insurance only, as these amounts are not paid until July. | 2019-07-10
7 | SCO | Life AND Health expenditures moved from FY 2019 to FY 2020 for pay period 14A. | SCO processes entries to move life AND health expenditures from FY 2019 to FY 2020 as this pay period is paid in July. | 2019-07-10
8 | SCO | Pay Plan Supplement Budget Journals Entered into STAR. | The completion of this task will depend on requisite approvals from the Joint Committee on Finance and the State Budget Office. | 2019-07-12
9 | SCO | Final Pension Obligation Bond charges recorded for FY 2019. |  | 2019-07-12
10 | SCO | ERA and HSA Administrative Fees Allocated by the SCO to appropriation 971 |  | 2019-07-12
11 | Agency | Process outstanding FY 2019 June and prior Interunit billing transactions (see inter-unit billing job aid) | See Popular Job Aids | 2019-07-12
12 | Agency | Procurement YEC Pre-Roll Tasks Completed | See Procurement YEC Work Center in STAR | 2019-07-18
13 | Agency | Complete year-end Travel Expense Tasks | See FY 2019 Travel Expense Closing Instructions | 2019-07-18
14 | Agency | Complete year-end Accounts Payable Tasks | See FY 2019 Accounts Payable Closing Instructions | 2019-07-18
15 | SCO | AP Closed for FY 2019 |  | 2019-07-18
16 | DOA | FY 2019 Purchase Order Roll |  | 7/20-7/21
17 | SCO | Completes final reconciliation of the AP Control Account (2000000). |  | 2019-07-26
18 | SCO | Completes final reconciliation of the AR Control Account (1351000). |  | 2019-07-26
19 | SCO | Completes final reconciliation of HR Accounting Line table in HCM with GL Payroll Journals. Differences are verified to pay period corrections, and detailed worksheet sent to those agencies with differences. |  | 2019-07-26
20 | Agency | Complete final reconciliation of expenses. | See Checklist in Section 18-01 WI Acctg Manual | 2019-07-26
21 | Agency | Complete final reconciliation of Benefits. | See Wisconsin Reconciliation Manual | 2019-07-26
22 | Agency | Process any remaining FY 2019 Interunit Transactions. | See Popular Job Aids | 2019-07-26
23 | Agency | Post all GL Journals that have been budget checked. | Query: WI_GL_JRNL_NOT_POSTED | 2019-07-26
24 | Agency | Complete NSF Fee Revenue entries in account 5999000. | Update pending to the Wisconsin Accounting Manual (see WiSMART Accounting Manual Section VI-7 for basic entries). | 2019-07-26
25 | Agency | PO increase justification worksheets due to the SCO (templates to be distributed by 7/12). |  | 2019-07-26
26 | SCO | SCO processes NSF revenue entries to transfer revenues from account 5999000 to the DOA GPR earned approriation. | Update pending to the Wisconsin Accounting Manual. | 2019-07-26
27 | Agency | Completes correcting/adjusting entries to all clearing appropriations - all balances cleared. | Job Aid: Enter and Process Journals | 2019-07-26
28 | Agency | Complete Non-statutory transfers/lapses | Instructions will be forthcoming from SCO to agencies; due date dependent on communications and compilation of information from State Budget Office
29 | SCO | SCO processes surplus property entries to transfer revenues from account 5950000 to the Budget Stabilization Fund |  | 2019-08-02
30 | SCO | FY 2019 Closed for all Non-Project Agencies |  | 2019-08-02
31 | Agency | Final Form 78 Certifications for Non-Project Agencies | Updated Form 78 User Guide Coming Soon | 2019-08-06
32 | Agency | Complete final reconciliation of Project Costing. | See Checklist in Section 18-01 WI Acctg Manual | 2019-08-07
33 | SCO | Project Costing closed for Project Agencies |  | 2019-08-07
34 | SCO | BI closed for Project Agencies |  | 2019-08-08
35 | SCO | AR closed for Project Agencies |  | 2019-08-08
36 | SCO | FY 2019 Closed for all agencies except for DOR. |  | 2019-08-09
37 | Agency | Final Form 78 Certifications for Project Agencies |  | 2019-08-13