## Year-End
State of Wisconsin
FY 2022 Year-End Closing and Reconciliation Task List |  |  |  |  | SCO Task
Agency Task
Module or Fiscal Year closing
No. | Entity | Task | Task Details | Due
1 | SCO | Continuing KK to GL reconciliation of expenditures, adjusting entries made. | This is an ongoing task. Any differences as of 6/30 will be adjusted by the SCO by 7/8. The SCO will continue to run reconciliations through 8/12 making sure all necessary adjustments are made. Agencies will be notified of all adjusting entries as they are made. NOTE: FY 2022 will be closed for Non-Project agencies on Friday, 8/5. So, the Friday, 7/29 KK to GL reconciliation should be the final substantive reconciliation before closing. The SCO will make a final check of all Non-Project agencies on Friday 8/5 to ensure that no additional issues were introduced that week. For Project Agencies, the final reconciliation will be 8/5, with a final check on 8/12. | ongoing
2 | SCO | Continuing analysis and reconciliation of Collected Revenue (CC_REV_COL) ledger. | This is an ongoing task. Any differences as of 06/30/2022 will be adjusted by SCO by 07/08/2022. Subsequently, the SCO will continue to run reconciliations through 8/12 making sure all necessary adjustments are made. Agencies can retreive these adjusting entries and the SCO's analysis by accessing the "Collected Revenue Analysis Register" available on the FY 2022 Closing page of the DOA website. NOTE: FY 2022 will be closed for Non-Project agencies on Friday, 8/5. So, Friday 07/29, Collected Revenue reconciliation should be the final substantive reconciliation before closing. The SCO will make a final check of all Non-Project agencies on Friday 8/5 to ensure that no additional issues were introduced that week. For Project Agencies, the final reconciliation will be 8/5, with a final check on 8/12. | ongoing
3 | Agency | Process all open vouchers, journals, interunit transactions as June 30th (see monthly SCO checklist). | See Section 18-01 of the Wisconsin Accounting Manual | 2022-07-01
4 | Agency | Review trial balance and flag accounts that appear incorrect. Created inventory of all clearing appropriations that need adjusting/correcting entries. | Reconciliation - Approach to Trial Balance Validation | 2022-07-01
5 | SCO | Life insurance expenditures reclassified to prepaids for pay period 11A. | SCO processes reclassification entries for life insurance only, as these amounts are not paid until July. | 2022-07-07
6 | SCO | Life insurance expenditures reclassified to prepaids for pay period 12B. | SCO processes reclassification entries for life insurance only, as these amounts are not paid until July. | 2022-07-07
7 | SCO | Life insurance expenditures reclassified to prepaids for pay period 13C. | SCO processes reclassification entries for life insurance only, as these amounts are not paid until July. | 2022-07-07
8 | SCO | Final Pension Obligation Bond charges recorded for FY 2022. |  | 2022-07-08
9 | SCO | ERA and HSA Administrative Fees Allocated by the SCO to appropriation 97100. |  | 2022-07-08
10 | Agency | Process outstanding FY 2022 June and prior Interunit billing transactions (see inter-unit billing job aid) | See Popular Job Aids | 2022-07-08
11 | SCO | Pay Plan Supplement Budget Journals Entered into STAR. | The completion of this task will depend on approvals from the Joint Committee on Finance and the State Budget Office. | 2022-07-12
12 | Agency | Procurement YEC Pre-Roll Tasks Completed | See Procurement YEC Work Center in STAR | 2022-07-14
13 | Agency | Complete year-end Travel Expense Tasks | See FY 2022 Travel Expense Closing Instructions | 2022-07-14
14 | Agency | Complete year-end Accounts Payable Tasks | See FY 2022 Accounts Payable Closing Instructions | 2022-07-14
15 | SCO | AP Closed for FY 2022 |  | 2022-07-14
16 | DOA | FY 2022 Purchase Order Roll |  | 7/16-7/17
17 | SCO | Pay Plan Supplement Budget Journals Entered into STAR. | The completion of this task will depend on approvals from the Joint Committee on Finance and the State Budget Office. | 2022-07-18
18 | SCO | Completes final reconciliation of the AP Control Account (2000000). |  | 2022-07-22
19 | SCO | Completes final reconciliation of the AR Control Account (1351000). |  | 2022-07-22
20 | SCO | Completes final reconciliation of HR Accounting Line table in HCM with GL Payroll Journals. Differences are verified to pay period corrections, and detailed worksheet sent to those agencies with differences. |  | 2022-07-22
21 | Agency | Complete final reconciliation of expenses. | See Checklist in Section 18-01 WI Acctg Manual | 2022-07-22
22 | Agency | Complete final reconciliation of Benefits. | See Wisconsin Reconciliation Manual | 2022-07-22
23 | Agency | Process any remaining FY 2022 Interunit Transactions. | See Popular Job Aids | 2022-07-22
24 | Agency | Post all GL Journals that have been budget checked. | Query: WI_GL_JRNL_NOT_POSTED | 2022-07-29
25 | Agency | Complete NSF Fee Revenue entries in account 5999000. | Update pending to the Wisconsin Accounting Manual (see WiSMART Accounting Manual Section VI-7 for basic entries). | 2022-07-29
26 | Agency | PO increase justification worksheets due to the SCO (templates to be distributed by 7/8). |  | 2022-07-29
27 | SCO | SCO processes NSF revenue entries to transfer revenues from account 5999000 to the DOA GPR earned approriation. | Update pending to the Wisconsin Accounting Manual. | 2022-07-29
28 | Agency | Completes correcting/adjusting entries to all clearing appropriations - all balances cleared. | Job Aid: Enter and Process Journals | 2022-07-29
29 | Agency | Complete Non-statutory transfers/lapses | Instructions sent out from SBO to agencies on June 8th; due dates are 7/29 for non-project agencies and 8/5 for project agencies
30 | SCO | SCO processes surplus property entries to transfer revenues from account 5950000 to the Budget Stabilization Fund |  | 2022-08-05
31 | SCO | FY 2022 Closed for all Non-Project Agencies |  | 2022-08-05
32 | Agency | Final Form 78 Certifications for Non-Project Agencies | Updated Form 78 User Guide Coming Soon | 2022-08-09
33 | Agency | Complete final reconciliation of Project Costing. | See Checklist in Section 18-01 WI Acctg Manual | 2022-08-10
34 | SCO | Project Costing closed for Project Agencies |  | 2022-08-10
35 | SCO | BI closed for Project Agencies |  | 2022-08-11
36 | SCO | AR closed for Project Agencies |  | 2022-08-12
37 | SCO | FY 2022 Closed for all agencies except for DOR. |  | 2022-08-12
38 | Agency | Final Form 78 Certifications for Project Agencies |  | 2022-08-16